## Pour Schedule
Concrete Pour Schedule
Type in the blue cells. Row 5 is an example — overwrite it. Status colors itself. Filter any column and the CY total in F3 follows what's visible.
|  |  |  | CY on visible rows: | 85
Date | Day | Job / Project | Job # | Pour / Placement | CY | Mix / PSI | Ready-Mix & Order # | Trucks × Spacing | Pump | Crew (Lead + Size) | Start | Status | Notes / Contacts | Week of (Mon) | CY
2026-09-14 | Mon | Riverside Distribution Center | 24-118 | Building 2 SOG — Pour 3 of 5 | 85 | 4000 PSI | Valley Ready-Mix #58821 | 9 × 40 min | 42m boom — on site 6:00 | M. Reyes + 6 | 7:00 | Confirmed | GC super J. Cole 555-0142 · gate B off Rt 9 | 2026-09-14 | 85
Blue = type the Monday; CY sums that week.

## How to Use
How to use this pour schedule
From Planning Ops — pour scheduling & crew planning built for concrete subs · planningops.com
1. One row per pour. Date, job, what you're pouring, yards, mix, and who's on it. Row 5 of the schedule is an example — overwrite it.
2. Type in the blue cells; the Day column and every total fill themselves.
3. Set Status from the dropdown: Scheduled → Confirmed → Complete, or Moved / Canceled. The color follows the status.
4. Confirm the day before: yards & mix with the plant, the pump, the crew, the start time. Re-check the site forecast at 4–6 AM and make the go/no-go call early enough to stop trucks.
5. Filter to any job or week — the 'CY on visible rows' total (F3) follows the filter. The Week-of block on the right totals each week you type a Monday for.
What this file can't do
It won't tell the plant, the pump, the GC, or your crew when a pour moves — you will, by phone, one call at a time. It can't see two crews booked on the same morning, and it shows no weather. When those start costing you pours, that's what Planning Ops is for: one click confirms, moves, or cancels a pour and notifies everyone on it.
planningops.com/blog/concrete-pour-schedule-template · Free to use and share within your company. © 2026 Planning Ops LLC