## 6-Week Lookahead
Six-Week Lookahead (make-ready)
Type the Monday week 1 starts in the blue cell — every week header fills itself. One row per activity: planned crew per week, and the constraint that has to clear before it can start.
Week 1 (Mon): | 2026-09-14
Job | Activity | Crew / responsible | Constraint to clear (material · RFI · inspection · access · crew) | Constraint owner / due
Riverside DC | B2 SOG — place & finish | Reyes + 6 | Vapor barrier on site by wk 2 | PM · 9/25 | 6 | 6
Riverside DC | B2 walls — form & pour | Parker + 4 | Embed RFI-14 answered | GC · 9/30 |  | 4 | 4 | 4
Cedar Port Bldg 1 | Footings — layout & pour | Ortiz + 5 | Footing inspection scheduled | Super · wk 4 |  |  |  | 5 | 5 | 5
Men committed / week

## How to Use
How to use this six-week lookahead
From Planning Ops — pour scheduling & crew planning built for concrete subs · planningops.com
1. Type the Monday week 1 starts in the blue cell (B4). The six week headers recalculate.
2. One row per activity — job, activity, crew, and the planned crew count in each week it runs. Rows 8–10 are examples; overwrite them.
3. The point of six weeks is make-ready: name the constraint that has to clear before each activity can start (material, RFI, inspection, access, crew) and who owns clearing it by when. An activity with an open constraint in week 2 is a problem today, not in week 2.
4. Roll it weekly: retype the Monday, drop the week that finished, plan the new week 6. Anything that moves into week 3 with its constraint still open goes on the three-week sheet as a risk.
5. The bottom row totals men committed per week — hold it against the crew you actually have, and hire or sequence early.
What this file can't do
It forgets last week the moment you roll the date, it can't see two rows claiming the same crew, and nobody is notified when a bar moves. When the roll and the conflicts start costing you, that's what the 90-day rolling Lookahead and the Projection board in Planning Ops are for — the lookahead that rolls itself and checks the crew math.
planningops.com/blog/three-week-lookahead-schedule · Free to use and share within your company. © 2026 Planning Ops LLC