## T&M Ticket
T&M Ticket
The field record of extra work, written and signed the day it happens. Blue cells are yours, orange cells calculate. Quantities only — price it on the Pricing tab in the office, never on the ticket the GC signs.
Ticket # | 014 | Date | 2026-09-15 | Type |  | T&M
Project | Riverside DC — Building 2 |  |  | Job # |  | 25-102
General contractor | GC name |  |  | GC ref |  | PCO-018
Directed by | R. Castor, GC superintendent |  |  | Area |  | Dock door 14
Description of work — what was done, not the argument about it
Saw-cut, removed and re-poured 180 SF of slab at dock door 14 after a scissor lift broke through the unsupported edge. Doweled into the existing slab, formed, placed and hard-troweled to match.
Why it’s extra | Damage by others — the GC’s lift broke the slab edge
Name | Classification | Crew / sub / temp | Company (sub or temp) | ST | OT | DT | Total hrs
J. Reyes | Foreman | Crew |  | 6 | 1.5
M. Ortiz | Finisher | Crew |  | 6 | 1.5
D. Parker | Operator | Crew |  | 4
T. Hicks | Laborer | Crew |  | 6
W. Cutler | Saw operator | Sub | Piedmont Saw & Core | 2.5
Totals
Equipment — unit / description |  |  |  | Hours
Walk-behind saw, 20 in. |  |  |  | 2.5
Skid steer #12 with breaker |  |  |  | 3
Ride-on power trowel |  |  |  | 1.5
Equipment hours
Materials — item |  |  |  | Qty | Unit | Delivery ticket #
Ready-mix 4000 psi |  |  |  | 4.5 | CY | QC-88231
#5 dowels, 18 in., epoxied |  |  |  | 36 | EA
Form lumber, 2x8 |  |  |  | 60 | LF
Cure & seal |  |  |  | 2 | GAL
Notes
Damaged edge photographed before demo. Lift unit SL-22 per the GC.
Photos taken (count) | 4
Contractor
Prepared by | J. Reyes, foreman |  |  | Date |  | 2026-09-15
Signature
GC representative
Name / title | R. Castor, superintendent |  |  | Date |  | 2026-09-15
Signature
Signature verifies the work, labor, equipment and materials listed on this ticket. Quantities only — pricing per contract.
planningops.com/blog/tm-ticket-template · Free to use and share within your company. © 2026 Planning Ops LLC

## T&M Log
T&M Ticket Log
Every ticket, one line each, from written to billed. Status drives the counts at the top. Hours are the ticket’s totals — they are already on that day’s daily report, so they are here to bill, never to pay again.
Tickets |  | Unsigned | Signed, not billed | Billed | Void | Labor hrs (not void) |  |  |  | Equipment hrs (not void)
Ticket # | Date of work | Project | Type | Description | Directed by | GC ref | ST | OT | DT | Labor hrs | Equip hrs | Signed by (GC) | Status | Sent to GC | COR / CO # | Billed | Notes
012 | 2026-09-08 | Riverside DC — Bldg 2 | Change Order | Thickened slab at rack anchor lines per RFI 31 — 6 in. extra depth, 3 ft wide | A. Fontaine, GC PM | RFI 31 | 30 | 1 |  |  | 10 | M. Templeton | Billed | 2026-09-08 | CO-07 | 2026-09-14
013 | 2026-09-10 | Riverside DC — Bldg 2 | T&M | Re-graded and re-compacted 2,400 SF of subgrade after the utility trench settled | J. Furr, GC super | PCO-011 | 22 | 3 |  |  | 11.5 | J. Furr | Signed | 2026-09-10 | COR-04 |  | Priced — waiting on the CO
014 | 2026-09-15 | Riverside DC — Bldg 2 | T&M | Saw-cut, removed and re-poured 180 SF of slab at dock door 14 | R. Castor, GC super | PCO-018 | 27.5 | 3 |  |  | 7 | R. Castor | Signed | 2026-09-15
004 | 2026-09-15 | Cedar Port Bldg 1 | Directed Extra | Crew and pump on standby 2.5 hrs while the electrician relocated conduit | M. Templeton, GC super |  | 15 |  |  |  | 2.5 |  | Unsigned | 2026-09-15 |  |  | Super off site — sent as written notice
005 | 2026-09-16 | Cedar Port Bldg 1 | T&M | Hand finishing around 26 sleeves added after layout | T. Beaver, GC super |  | 6 | [5 empty] | Draft

## Pricing (office)
Pricing Worksheet (office only)
Prices the ticket on the T&M Ticket tab for your change order request. Quantities come across on their own; type your contract’s rates and markup in the blue cells. The rates shown are examples. This sheet never goes on the ticket the GC signs.
Ticket # |  | Project
Name | Classification | ST hrs | ST rate | OT hrs | OT rate | DT hrs | DT rate | Extended
|  |  | 68.5 |  | 102.75
|  |  | 58 |  | 87
|  |  | 62 |  | 93
|  |  | 44 |  | 66
85
Labor
Equipment |  | Hours | Rate / hr |  |  |  |  | Extended
45
95
38
Equipment
Materials |  | Qty | Unit | Unit cost |  |  |  | Extended
168
6.4
1.15
38
Materials
Change order request
| Subtotal | Markup % | Markup | Total
Labor
Equipment
Materials
Total
Markup % comes from your contract (it often differs for labor, equipment and materials, and for sub work). Leave it blank if the contract rates already include it.

## How to Use
How to use the T&M ticket template
From Planning Ops — operations software built for concrete subs · planningops.com
1. T&M Ticket tab: one ticket per piece of extra work, per day. Fill the header — ticket number, date, type, project, the GC, who directed the work and the GC’s reference (PCO, RFI or ASI number). The examples are there to overwrite.
2. Describe the work, not the argument: what was done, where, and why it is extra (out of scope, damage by others, standby caused by others, or a directed change). One sentence of cause beats a paragraph of blame.
3. Labor: one line per person with Straight Time, Overtime and Double Time on this extra work only. Subs and temps get their company. Equipment in hours, materials with quantity, unit and the delivery ticket number.
4. Print it (one page, portrait) and get the GC representative’s name, title and signature before the crew leaves. Sign it yourself. If nobody from the GC will sign, send it the same day anyway as written notice — and check your subcontract’s notice clause for the deadline.
5. T&M Log tab: add the ticket the day it is written. Move the Status as it goes — Draft, Unsigned, Signed, Billed, or Void (keep the number; never reuse it). The counts at the top show what is still unsigned and what is signed but not billed.
6. Pricing (office) tab: quantities come across from the ticket on their own. Type your contract’s labor, equipment and material rates and the markup, and the change order request total calculates. Save a copy of the file per ticket, or copy the tab.
What this file can't do
A spreadsheet can’t get the GC’s signature on the slab, number tickets per project for you, or stop a signed ticket from being edited afterwards — and the hours on it get typed again from the daily report. In Planning Ops, the foreman writes the ticket on the phone or tablet, the GC’s rep signs with a finger, it locks with the project’s next number and emails as a branded PDF, and the office sees Unsigned, Signed and Billed on one log that exports to Excel. Ticket hours never post to payroll a second time.
planningops.com/blog/tm-ticket-template · Free to use and share within your company. © 2026 Planning Ops LLC