## 2-Week Lookahead
Two-Week Lookahead
Type the Monday this lookahead starts in the blue cell — every date fills itself. One row per activity; put the crew count (or an X) in each working day.
Week of (Mon): | 2026-09-14
Job | Activity | Crew / responsible
Riverside DC | B2 SOG — place & finish | Reyes + 6 | 6 | 6
Riverside DC | B2 walls — form & pour | Parker + 4 |  |  | 4 | 4
Men committed / day

## How to Use
How to use this two-week lookahead
From Planning Ops — pour scheduling & crew planning built for concrete subs · planningops.com
1. Type the Monday this lookahead starts in the blue cell (B4). Every day header and both week bands recalculate.
2. One row per activity — job, the activity in field language, and whose crew it is. Rows 8–9 are examples; overwrite them.
3. Put the planned crew count in each working day (or an X if you don't plan by headcount). The bottom row totals men committed per day.
4. Run it weekly: each Monday, retype the new start date — week 2 becomes week 1, and you plan the new week 2. Two weeks is the horizon when the GC runs a two-week meeting or the job turns fast; go to three when week two keeps surprising you.
5. Print it landscape for the coordination meeting; it fits one page wide.
What this file can't do
It forgets last week the moment you roll the date, it can't see two rows claiming the same crew, and nobody is notified when a bar moves. When the roll and the conflicts start costing you, that's what the 90-day rolling Lookahead and the Projection board in Planning Ops are for — the lookahead that rolls itself and checks the crew math.
planningops.com/blog/three-week-lookahead-schedule · Free to use and share within your company. © 2026 Planning Ops LLC