## Weekly Lookahead
Weekly Lookahead
Type the Monday this lookahead starts in the blue cell — every date fills itself. One row per activity; put the crew count (or an X) in each working day.
Week of (Mon): | 2026-09-14
Job | Activity | Crew / responsible |  |  |  |  | Notes / constraints
Riverside DC | B2 SOG — place & finish | Reyes + 6 | 6 | 6 |  |  | Pump booked 6 AM · inspection Tue
Riverside DC | B2 walls — form & pour | Parker + 4 |  |  | 4 | 4 | Rebar delivery Wed AM
Men committed / day

## How to Use
How to use this weekly lookahead
From Planning Ops — pour scheduling & crew planning built for concrete subs · planningops.com
1. Type the Monday in the blue cell (B4). The six day headers recalculate.
2. One row per activity — job, the activity in field language, whose crew it is, and the crew count per day. Rows 8–9 are examples; overwrite them.
3. Use the Notes / constraints column for what has to be true for the day to happen — pump booked, inspection passed, rebar on site.
4. This is the foremen's week, firm by Friday for the week after. Plan the weeks beyond it on the two- or three-week version; this sheet is the slice you hand out.
5. Print it landscape; it fits one page.
What this file can't do
It forgets last week the moment you roll the date, it can't see two rows claiming the same crew, and nobody is notified when a bar moves. When the roll and the conflicts start costing you, that's what the 90-day rolling Lookahead and the Projection board in Planning Ops are for — the lookahead that rolls itself and checks the crew math.
planningops.com/blog/three-week-lookahead-schedule · Free to use and share within your company. © 2026 Planning Ops LLC