## Weekly Report
Weekly Manpower Report
Type the Monday in the blue date cell — every day header fills itself. One row per job or crew: men on site each working day, the men-days you planned, and the hours. Totals and the summary write themselves.
Week of (Mon): | 2026-09-14 | Contractor: | Your Company Concrete |  |  | Prepared by: | Ops manager |  |  | Sent to: | GC super · PM
Job / project | Crew / foreman | Trade / classification | [6 empty] | Men-days (actual) | Men-days (planned) | Variance | ST hours | OT hours | Work performed / notes
[10 empty] | from look-ahead | actual − plan | straight | overtime
Riverside DC | Reyes + 6 | Place & finish | 7 | 7 | 7 | 0 | 6 | 0 |  | 34 |  | 240 | 12 | B2 SOG placed Tue (412 CY) · Thu rained out
Riverside DC | Parker + 4 | Form & rebar | 5 | 5 | 5 | 5 | 5 | 0 |  | 25 |  | 200 | 0 | B3 walls formed, pour set for Mon
Cedar Port Bldg 1 | Ortiz + 5 | Footings | 0 | 0 | 6 | 6 | 6 | 4 |  | 24 |  | 176 | 8 | Footings F1–F9 poured Fri · Sat strip
Men on site / day
This week at a glance
Men-days worked |  |  | sum of every man on site, every day
Men-days planned |  |  | from the look-ahead you sent Monday
Variance to plan |  |  | positive = more men than planned
Peak day (men) |  |  | the day the yard, the trucks and the parking had to hold
Average men / working day |  |  | men-days ÷ days anyone worked
Total hours (ST + OT)
Overtime share |  |  | over ~10% for a month is a crew-size conversation, not a scheduling one

## Daily Log
Daily Manpower Log
One line per crew per day, from the foreman’s daily report. Total hours calculates. Add the men per day into the Weekly Report tab on Friday — or keep this tab as the daily manpower report the GC asks for.
Date | Job / project | Crew / foreman | Trade / classification | Men on site | ST hours | OT hours | DT hours | Total hours | Work performed / area | Weather · delays · visitors
2026-09-14 | Riverside DC | Reyes + 6 | Place & finish | 7 | 56 | 0 | 0 |  | Clear 68°F · pump on site 6 AM
2026-09-14 | Riverside DC | Parker + 4 | Form & rebar | 5 | 40 | 0 | 0
2026-09-15 | Riverside DC | Reyes + 6 | Place & finish | 7 | 56 | 12 | 0 |  | Clear 71°F · finished 6:40 PM
Totals

## How to Use
How to use this weekly manpower report
From Planning Ops — pour scheduling & crew planning built for concrete subs · planningops.com
1. Weekly Report tab: type the Monday in the blue date cell (B4). The six day headers fill themselves. Fill in the contractor, who prepared it, and who it goes to.
2. One row per job or crew — whichever way your GC wants it cut. Rows 8–10 are examples; overwrite them. Put the men on site in each working day; leave a day blank when nobody worked.
3. Men-days (planned) comes from the look-ahead you sent on Monday — the crew count per day, added up. The variance column then shows where the week drifted from the plan, row by row.
4. ST and OT hours come off the timesheets or the daily reports. The summary block under the totals reads the whole week: men-days, peak day, average per day, hours, and the overtime share.
5. Daily Log tab: one line per crew per day, from the foreman’s daily report — men, ST/OT/DT, what got done, weather and delays. Total hours calculates. This tab IS the daily manpower report if the GC wants one; the Weekly Report is what you send Friday.
6. Close it the same day every week. A report that skips a week stops being a record. Print landscape; each tab fits one page wide.
What this file can't do
Every number on it was typed somewhere else first — the foreman’s daily report, the timesheet, the look-ahead — so the week gets keyed two or three times, and nothing checks the men on the report against the roster or the crew you actually scheduled. When that starts costing you, it is what the Manpower board in Planning Ops is for: the crew you schedule prefills the foreman’s daily report, his submitted hours flow back into time tracking, and the branded Excel export and the Distribute email come off the same board — nothing typed twice.
planningops.com/blog/weekly-manpower-report-template · Free to use and share within your company. © 2026 Planning Ops LLC